## Sheet1
Coldwell Banker - Android Development Tasks & Checkpoints
Major Features: | Components: | Status: | Outstanding Task: | Resource: | Time:
Get Started
| Intro Page | I | Update copy | Amar | 2014-08-15
| Login | C
| Create Account | C
| Agent Login | O |  | Amar | 2014-08-15
| Share Experience | I | Page is implemented but needs to be tied together with services and made fully functional. | Amar | 2014-08-15
| Welcome User | C
Navigation Drawer
| Buyer Options | I |  | Amar | 2014-08-08
| Buyer/Seller Options | I |  | Amar | 2014-08-08
| Seller Options | I |  | Amar | 2014-08-08
| Agent Options | I |  | Amar | 2014-08-08
Buyer/Seller Homescreen & Menu Options
| Home Gallery | I | Default Image | Steve | 2014-08-08
| My Listings | O |  | Steve | 2014-08-15
| My Neighborhood | O |  | Steve | 2014-08-15
| My Favorites | O | Do service call & display appropriate screen/data. | Mark | 2014-08-11
| Recommended For Me | O |  | Steve | 2014-08-15
| New Listings in My Area | O |  | Steve | 2014-08-15
| Messages | O |  | Steve | 2014-08-15
| Activity Feed Updates | O |  | Steve | 2014-08-15
Agent Homescreen & Menu Options
| Home Gallery | I |  | Steve | 2014-08-22
| My Listings | O |  | Steve | 2014-08-22
| New Messages & Comments | O |  | Steve | 2014-08-22
| Listings In My Office | O | Do service call & display appropriate screen/data. | Steve | 2014-08-22
Property Search
| Search Results | I | Clean up & bug fixes. | Steve | 2014-08-12
| Property Detail | I | Styling the existing screen. | Mark | 2014-08-12
| Advanced Search | I | Style tabs. Implement Property Features. Implement Language & Specielties. | Steve | 2014-08-12
Agent Search
| Agent Results Page | I | Clean up & outstanding items. InfoWindow Bug Fix | Steve | 2014-08-12
| Agent Detail | I | Styling of existin Screen | Mark | 2014-08-12
Office Search
| Office Results Page | I | Clean up & outstanding items. | Steve | 2014-08-12
| Office Detail | I | Styling of existin Screen | Mark | 2014-08-12
| Office Misc. (outstanding) | I
Team Search
| Team Results Page | O
Buyer/Seller Activity Feed |  | O |  | Amar | 2014-08-12
Buyer/Seller My Neighborhood |  | O |  | Steve
Buyer/Seller Favorites |  | I |  | Steve
Buyer/Seller Recommended For Me |  | O |  | Steve
Buyer/Seller Messages |  | O |  | Amar | 2014-08-15
Buyer/Seller My Agent |  | O |  | Steve
Buyer/Seller My Searches |  | O |  | Amar | 2014-08-19
Buyer and/or Seller Profile
| Contact Info | O |  | Amar | 2014-08-22
| My Notes | O |  | Amar | 2014-08-22
| Property Listings | O |  | Amar | 2014-08-22
| Connections | O |  | Amar | 2014-08-22
| Comments & Messages | O |  | Amar | 2014-08-22
| Searches | O |  | Amar | 2014-08-22
| Page Views | O |  | Amar | 2014-08-22
| Favorites | O |  | Amar | 2014-08-22
| Shares | O |  | Amar | 2014-08-22
| Driving Directions | O |  | Amar | 2014-08-22
| Printed Pages | O |  | Amar | 2014-08-22
| My Agent | O |  | Amar | 2014-08-22
| Activity Feed Notification |  |  | Amar | 2014-08-22
Camera |  | O |  | Amar | 2014-08-15
Photos & Videos |  | O |  | Amar | 2014-08-15
Seller Analytics |  | O |  | Amar | 2014-08-29
Agent My Listings |  | O |  | Steve | 2014-08-29
Agent New Office Listings |  | O |  | Steve | 2014-08-29
Agent New Area Listings |  | O |  | Steve | 2014-08-29
Agent My Connections |  | O |  | Amar | 2014-08-29
Agent Recommended Properties |  | O |  | Amar | 2014-08-29
Miscellaneous
| Network Error Strategy |  |  | Steve/Amar | 2014-08-29